EduTrack

Home Education, Evidenced.

Agile Delivery Plan · Implementation Phasing · Full Sprint Backlog

| Document Type | Agile Delivery Plan — Implementation Phasing & Sprint Backlog |
| --- | --- |
| Project | EduTrack — UK Home Education Management Platform |
| Stack | Django 5 · Bootstrap 5 · Neon Postgres · Cloudinary · Heroku |
| Total Sprints | 4 Sprints + Sprint 0 (Foundation) across 12 working days |
| Methodology | Agile Scrum · GitHub Projects · Conventional Commits |
| Delivery Agent | Claude — planning, stories, implementation, testing, QA |

# 1. How To Use This Document

This document is your single operating manual from first commit to final deployment. It defines every epic, every user story, every acceptance criterion, every task, and every commit — in the exact order they should be executed. Nothing is ambiguous. Nothing requires guessing.

## 1.1 The Working Protocol

Every session with Claude follows this sequence, without exception:

| Step | Protocol Action |
| --- | --- |
| 1 | Open this document to the current story |
| 2 | Tell Claude: "We are working on [STORY-ID]: [Title]" |
| 3 | Claude reads the story, AC, tasks, and DoD before writing any code |
| 4 | Claude implements only the tasks listed — nothing more, nothing less |
| 5 | Each task = one commit. Commit message is specified in the task. |
| 6 | After each commit: confirm it works before moving to the next task |
| 7 | When all tasks are done: run the AC checklist. All must pass. |
| 8 | Mark the story Done on GitHub Projects. Move to next story. |

## 1.2 Global Definitions

### Definition of Ready (DoR) — applies to every story before work begins

A story is READY when: (1) It has a clear user story statement. (2) Acceptance criteria are written and unambiguous. (3) All tasks are broken into single-commit chunks. (4) Dependencies (prior stories) are Done. (5) The developer understands what "done" looks like.

### Definition of Done (DoD) — applies to every story before it is marked Done

A story is DONE when: (1) All acceptance criteria pass. (2) Code follows PEP 8; has docstrings on all functions. (3) No hardcoded secrets. (4) All templates pass W3C HTML validation. (5) Commit history is clean with conventional commit messages. (6) If a form: validation tested with invalid inputs. (7) If a view: access control tested manually. (8) README updated if the story adds a new feature or config.

### Commit Convention — every commit must follow this format

feat(app): New feature or user-visible behaviour fix(app): Bug fix test(app): Adding or updating automated tests docs: README, docstrings, inline comments style: CSS/template changes, no logic change chore: Config, dependencies, environment setup refactor(app): Code restructure, no behaviour change Examples: feat(scheduler): implement 180-day lesson distribution algorithm feat(accounts): add role-based registration with parent/student roles fix(tracker): mastery score not persisting on modal close test(accounts): add role access control test cases chore: configure Cloudinary storage backend docs(readme): add deployment section

## 1.3 Sprint Structure Overview

| Sprint | Days | Stories | Theme | Deploy |
| --- | --- | --- | --- | --- |
| Sprint 0 | Days 1–3 | 8 stories | Foundation: project skeleton, models, seed data, admin, first deploy | 🚀 DEPLOY — empty shell live on Heroku |
| Sprint 1 | Days 4–6 | 10 stories | Auth & Scheduling: registration, login, child setup, auto-scheduler | 🚀 DEPLOY — parent can register and generate a schedule |
| Sprint 2 | Days 7–9 | 12 stories | Calendar & Tracking: weekly view, lesson modal, mastery, evidence | 🚀 DEPLOY — full student lesson interaction loop working |
| Sprint 3 | Days 10–12 | 10 stories | Reports, Stripe, Tests, Docs, Final Deploy | 🚀 FINAL DEPLOY — production-ready, all LOs evidenced |

# 2. Epic Map

Nine epics cover the full product. Each epic maps to a GitHub Projects milestone. Stories are assigned to epics via the milestone field.

| Epic | Name | Sprint | Stories | LO Coverage |
| --- | --- | --- | --- | --- |
| E1 | Project Foundation | Sprint 0 | S0.1–S0.8 | LO1.2, LO2.1, LO5.1, LO5.2, LO6.1, LO6.3 |
| E2 | Authentication & Roles | Sprint 1 | S1.1–S1.4 | LO3.1, LO3.2, LO3.3 |
| E3 | Child Setup & Scheduling | Sprint 1 | S1.5–S1.10 | LO1.4, LO2.2, LO2.3, LO2.4, LO7.1 |
| E4 | Calendar View | Sprint 2 | S2.1–S2.3 | LO1.1 |
| E5 | Lesson Tracking | Sprint 2 | S2.4–S2.9 | LO2.2, LO2.3, LO2.4 |
| E6 | Evidence & Files | Sprint 2 | S2.10–S2.12 | LO2.2 |
| E7 | Reports & LA Sharing | Sprint 3 | S3.1–S3.3 | LO2.2, LO2.4, LO3.1, LO3.3 |
| E8 | Payments (Stripe Stub) | Sprint 3 | S3.4–S3.5 | LO1.1, LO2.2 |
| E9 | Testing, Docs & Deploy | Sprint 3 | S3.6–S3.10 | LO1.5, LO4.1, LO4.2, LO4.3, LO6.1, LO6.2, LO8 |

SPRINT 0 — Project Foundation Days 1–3 · Epic E1 · 8 Stories · Target: Live empty shell on Heroku by end of Day 3

Sprint Goal: Create the smallest possible deployable Django application. All 7 models exist and are migrated. Oak curriculum data is seeded. Django admin is configured. The app is live on Heroku with DEBUG=False. No features, no auth, no pages — just a solid, deployable foundation.

| S0.1 — Django Project Skeleton |  |
| --- | --- |
| User Story | As a developer, I can create the initial Django project structure with all apps registered so that every subsequent story has a clean, consistent codebase to build on |
| LO Covered | LO5.1, LO5.2 |
| Acceptance Criteria | ✓ Running `python manage.py check` returns no errors ✓ Six apps exist: accounts, curriculum, scheduler, tracker, reports, payments ✓ All apps are registered in INSTALLED_APPS ✓ settings.py uses python-decouple for all sensitive values ✓ A .env.example file is committed with all required keys (no values) ✓ .gitignore correctly excludes .env, *.pyc, __pycache__, db.sqlite3, media/ |
| Tasks | ☐ feat(chore): django-admin startproject edutrack . → commit: "chore: initialise Django project" ☐ feat(chore): create accounts, curriculum, scheduler, tracker, reports, payments apps → commit: "chore: create six Django application modules" ☐ feat(chore): configure settings.py with python-decouple; create .env and .env.example → commit: "chore: configure environment variable management with python-decouple" ☐ feat(chore): create .gitignore, add README.md skeleton with project title → commit: "chore: add gitignore and readme skeleton" ☐ feat(chore): git init, create GitHub repo, push initial commit → commit: (first push) |
| Definition of Done | All 6 apps registered. `manage.py check` passes. GitHub repo exists. No secrets in any committed file. |

| S0.2 — Database Configuration |  |
| --- | --- |
| User Story | As a developer, I can connect the Django project to the Neon Postgres database so that all models can be migrated and the app has a persistent data store |
| LO Covered | LO1.2, LO5.2, LO6.3 |
| Acceptance Criteria | ✓ DATABASE_URL is read from environment variables, never hardcoded ✓ Running `python manage.py migrate` completes without errors ✓ dj-database-url and psycopg2-binary are in requirements.txt ✓ A requirements.txt file exists with all dependencies pinned |
| Tasks | ☐ chore: pip install django dj-database-url psycopg2-binary python-decouple gunicorn whitenoise → commit: "chore: add core dependencies to requirements.txt" ☐ chore: configure DATABASES in settings.py using dj-database-url and decouple → commit: "chore: configure Neon Postgres database connection" ☐ chore: run initial migrate to create Django system tables → commit: "chore: run initial Django migrations" |
| Definition of Done | Database connects. `manage.py migrate` succeeds. DATABASE_URL only in .env, never in code. |

| S0.3 — Cloudinary Storage Configuration |  |
| --- | --- |
| User Story | As a developer, I can connect Cloudinary as the media file storage backend so that all file uploads in later sprints work correctly in both development and production |
| LO Covered | LO6.1, LO6.3 |
| Acceptance Criteria | ✓ CLOUDINARY_URL is read from environment, never hardcoded ✓ DEFAULT_FILE_STORAGE is set to django-cloudinary-storage ✓ cloudinary and django-cloudinary-storage are in requirements.txt ✓ A test upload via Django shell confirms Cloudinary connectivity |
| Tasks | ☐ chore: pip install cloudinary django-cloudinary-storage Pillow → commit: "chore: add Cloudinary and Pillow dependencies" ☐ chore: configure DEFAULT_FILE_STORAGE and CLOUDINARY settings in settings.py → commit: "chore: configure Cloudinary as default media storage backend" |
| Definition of Done | Cloudinary configured. CLOUDINARY_URL in .env only. No test files committed. |

| S0.4 — All Seven Custom Models |  |
| --- | --- |
| User Story | As a developer, I can define all seven custom data models with fields, relationships, and constraints so that the complete data architecture exists in code and can be migrated in one step |
| LO Covered | LO1.2, LO2.1, LO7.1 |
| Acceptance Criteria | ✓ All 7 models created: UserProfile, Lesson, Child, EnrolledSubject, ScheduledLesson, LessonLog, EvidenceFile, Report ✓ All ForeignKey and OneToOne relationships are correctly defined ✓ All CharField fields have max_length; all nullable fields have null=True, blank=True ✓ All choice fields use Django choices pattern with named constants ✓ Running `manage.py makemigrations` then `migrate` succeeds with zero errors ✓ Every model has a `__str__` method returning a human-readable string ✓ Every model has a docstring explaining its purpose |
| Tasks | ☐ feat(accounts): define UserProfile model with role choices → commit: "feat(accounts): add UserProfile model with parent/student/admin role choices" ☐ feat(curriculum): define Lesson model with all Oak CSV fields → commit: "feat(curriculum): add Lesson model for Oak National Academy curriculum data" ☐ feat(scheduler): define Child model with parent FK and student_user link → commit: "feat(scheduler): add Child model with parent relationship" ☐ feat(scheduler): define EnrolledSubject model with pace and colour fields → commit: "feat(scheduler): add EnrolledSubject model with lessons_per_week and colour" ☐ feat(scheduler): define ScheduledLesson model linking child, lesson, date → commit: "feat(scheduler): add ScheduledLesson model for auto-generated timetable" ☐ feat(tracker): define LessonLog model with status, mastery, notes → commit: "feat(tracker): add LessonLog model with status and mastery score" ☐ feat(tracker): define EvidenceFile model with Cloudinary field → commit: "feat(tracker): add EvidenceFile model with Cloudinary upload field" ☐ feat(reports): define Report model with UUID share token → commit: "feat(reports): add Report model with share_token for LA access" ☐ chore: run makemigrations and migrate for all apps → commit: "chore: generate and apply initial migrations for all models" |
| Definition of Done | All 7 models migrated. `manage.py check` passes. Every model has __str__ and docstring. Zero hardcoded values. |

| S0.5 — Django Admin Configuration |  |
| --- | --- |
| User Story | As a admin, I can manage all application data through the Django admin panel so that I can perform all data management tasks and customer support actions without a separate interface |
| LO Covered | LO3.1 |
| Acceptance Criteria | ✓ All 7 models are registered and visible in the admin panel ✓ UserAdmin is extended to show role and avatar fields ✓ List displays show meaningful columns (not just object ID) ✓ Search and filter are configured on key fields ✓ Admin panel is accessible at /admin/ with superuser credentials |
| Tasks | ☐ feat(accounts): register UserProfile in admin with custom UserAdmin showing role field → commit: "feat(accounts): configure UserAdmin with role and profile fields" ☐ feat(curriculum): register Lesson with list_display, search_fields, list_filter → commit: "feat(curriculum): configure Lesson admin with search and filter" ☐ feat(scheduler): register Child, EnrolledSubject, ScheduledLesson in admin → commit: "feat(scheduler): register scheduler models in Django admin" ☐ feat(tracker): register LessonLog and EvidenceFile in admin → commit: "feat(tracker): register tracker models in Django admin" ☐ feat(reports): register Report in admin with share_token visible → commit: "feat(reports): register Report model in Django admin" ☐ chore: create superuser via manage.py createsuperuser → (local only, no commit needed) |
| Definition of Done | All 7 models visible in admin. Superuser can log in. List views show meaningful data. |

| S0.6 — Oak Curriculum Seed Command |  |
| --- | --- |
| User Story | As a developer, I can load the Oak National Academy CSV data into the database with a single management command so that the full 10,055-row curriculum dataset is available for subject selection and scheduling |
| LO Covered | LO1.4 |
| Acceptance Criteria | ✓ A management command `seed_curriculum` exists at curriculum/management/commands/seed_curriculum.py ✓ Running `python manage.py seed_curriculum --file path/to/file.csv` loads all rows ✓ The command is idempotent: running twice does not create duplicates (uses get_or_create) ✓ The command prints a progress summary on completion ✓ Running the command on the full 10,055-row CSV completes without errors ✓ The command has a docstring explaining its purpose and arguments |
| Tasks | ☐ feat(curriculum): create management command scaffold at curriculum/management/commands/seed_curriculum.py → commit: "feat(curriculum): scaffold seed_curriculum management command" ☐ feat(curriculum): implement CSV reading and Lesson.objects.get_or_create logic with bulk-friendly batching → commit: "feat(curriculum): implement CSV ingestion with idempotent get_or_create" ☐ feat(curriculum): add progress output and row count summary → commit: "feat(curriculum): add progress logging to seed_curriculum command" ☐ chore: run seed_curriculum locally and verify row count in admin → (local verification, no commit) |
| Definition of Done | seed_curriculum runs clean. 10,055 Lesson records exist in DB. Running twice = no duplicates. Command documented. |

| S0.7 — Base Template and Static Files |  |
| --- | --- |
| User Story | As a developer, I can create a base HTML template with Bootstrap 5, a navbar shell, a messages block, and static file configuration so that every page built in subsequent sprints inherits a consistent, accessible layout |
| LO Covered | LO1.1 |
| Acceptance Criteria | ✓ base.html exists in templates/ and extends Bootstrap 5 via CDN ✓ Navbar includes logo/brand name, placeholder nav links, empty user area (right side) ✓ Django messages block renders success, error, warning, info with Bootstrap alert classes ✓ A {% block content %} is defined for child template override ✓ Static files are configured: STATIC_URL, STATICFILES_DIRS, whitenoise middleware ✓ A custom.css file exists at static/css/custom.css with CSS variable palette defined ✓ A homepage view at / renders a base-extending template with "EduTrack — Coming Soon" ✓ W3C HTML validation passes on the rendered homepage |
| Tasks | ☐ chore: configure TEMPLATES, STATIC settings, add whitenoise to MIDDLEWARE → commit: "chore: configure templates and static file serving with whitenoise" ☐ feat(templates): create base.html with Bootstrap 5 CDN, navbar shell, messages block, content block → commit: "feat(templates): add base.html with Bootstrap 5 and messages support" ☐ style: create static/css/custom.css with CSS variable palette (--primary, --secondary, etc.) → commit: "style: add custom CSS with colour system variables" ☐ feat(edutrack): add homepage view, URL, and minimal extends-base template → commit: "feat(edutrack): add homepage placeholder view and template" |
| Definition of Done | Homepage renders. Bootstrap styles load. Messages block exists. CSS variables defined. W3C validation passes. |

| S0.8 — First Heroku Deployment |  |
| --- | --- |
| User Story | As a developer, I can deploy the application skeleton to Heroku and verify it runs in production so that we have a live URL from Day 3 onwards and all subsequent sprints deploy to a real environment |
| LO Covered | LO6.1, LO6.2, LO6.3, LO5.2 |
| Acceptance Criteria | ✓ Procfile exists with correct gunicorn command ✓ runtime.txt specifies Python version ✓ All Heroku Config Vars are set (no secrets in code) ✓ The app is accessible at its Heroku URL ✓ Django admin is accessible and functional on the live URL ✓ DEBUG=False in production; ALLOWED_HOSTS includes .herokuapp.com ✓ Running `heroku run python manage.py migrate` succeeds ✓ Running `heroku run python manage.py seed_curriculum` loads all 10,055 rows ✓ No 500 errors on the homepage |
| Tasks | ☐ chore: create Procfile with web: gunicorn edutrack.wsgi and runtime.txt → commit: "chore: add Procfile and runtime.txt for Heroku deployment" ☐ chore: set DEBUG, ALLOWED_HOSTS, SECURE settings for production in settings.py → commit: "chore: configure production security settings" ☐ chore: heroku create, set all Config Vars, git push heroku main → commit: "chore: initial Heroku deployment" ☐ chore: heroku run python manage.py migrate && seed_curriculum → (Heroku CLI, no commit) ☐ chore: heroku run python manage.py createsuperuser → (Heroku CLI, no commit) ☐ chore: smoke test — open live URL, verify admin, verify no errors → commit: "chore: verify Sprint 0 deployment — shell live on Heroku" |
| Definition of Done | App live on Heroku. Admin accessible. 10,055 lessons seeded. DEBUG=False. No secrets in repo. Homepage loads. |

SPRINT 1 — Authentication, Child Setup & Scheduling Days 4–6 · Epics E2 & E3 · 10 Stories · Target: Parent registers, adds child, auto-schedule generates

Sprint Goal: A parent can register with a parent role, log in, add a child, select Oak subjects with a weekly pace, and generate a fully auto-scheduled 180-day timetable. A student login is created by the parent. All role-based access is enforced.

| S1.1 — Parent Registration |  |
| --- | --- |
| User Story | As a parent, I can register an account with my email and password so that I can access the platform and begin managing my child's home education |
| LO Covered | LO3.1, LO2.4 |
| Acceptance Criteria | ✓ Registration form has: email, first name, last name, password, confirm password ✓ Submitting valid data creates a User and a UserProfile with role="parent" ✓ Duplicate email shows a clear validation error message ✓ Password shorter than 8 characters is rejected with a helpful message ✓ After successful registration, user is redirected to dashboard with a success message ✓ Registration page is accessible at /accounts/register/ ✓ W3C HTML validation passes on registration page |
| Tasks | ☐ feat(accounts): create CustomUserCreationForm extending UserCreationForm with email field → commit: "feat(accounts): add parent registration form with email" ☐ feat(accounts): create register view — on valid POST create User + UserProfile(role=parent), login, redirect → commit: "feat(accounts): add registration view with automatic parent role assignment" ☐ feat(accounts): add register URL to accounts/urls.py and include in project urls.py → commit: "feat(accounts): wire registration URL" ☐ feat(templates): create accounts/register.html extending base.html with crispy form → commit: "feat(templates): add registration page template" |
| Definition of Done | Registration creates User + UserProfile(role=parent). Validation errors display. Redirect with success message. No duplicate users possible. |

| S1.2 — Login, Logout & Login State |  |
| --- | --- |
| User Story | As a user, I can log in and out of the application so that I can access my role-appropriate pages and my login state is always visible |
| LO Covered | LO3.1, LO3.2 |
| Acceptance Criteria | ✓ Login form at /accounts/login/ accepts email and password ✓ Incorrect credentials show a clear error message ✓ After login, the navbar shows the user's first name and role badge (e.g. "Parent" or "Student") ✓ Logout at /accounts/logout/ clears the session and redirects to homepage ✓ Unauthenticated users accessing protected URLs are redirected to login with next parameter ✓ After login, user is redirected to the appropriate dashboard for their role |
| Tasks | ☐ feat(accounts): configure Django LoginView with custom template and email-based auth → commit: "feat(accounts): add login view with email authentication" ☐ feat(accounts): add logout view with redirect to homepage → commit: "feat(accounts): add logout view" ☐ feat(templates): create accounts/login.html with crispy form and error display → commit: "feat(templates): add login page template" ☐ feat(templates): update base.html navbar — show first name + role badge when authenticated, login/register links when not → commit: "feat(templates): reflect login state in navbar with name and role badge" ☐ feat(accounts): configure LOGIN_URL, LOGIN_REDIRECT_URL, LOGOUT_REDIRECT_URL in settings.py → commit: "feat(accounts): configure login/logout redirect URLs" |
| Definition of Done | Login works. Logout clears session. Navbar shows name+role when logged in. Unauthenticated redirect to login works. |

| S1.3 — Role-Based Access Decorator |  |
| --- | --- |
| User Story | As a developer, I can create a reusable role_required decorator that restricts views by user role so that every protected view can declare its required role in one line and enforce it consistently |
| LO Covered | LO3.3, LO1.4 |
| Acceptance Criteria | ✓ A decorator `role_required(role)` exists in accounts/decorators.py ✓ Applying @role_required("parent") to a view redirects students to their dashboard with an error message ✓ Applying @role_required("student") to a view redirects parents to their dashboard with an error message ✓ Unauthenticated users hitting any decorated view are redirected to login ✓ The decorator is documented with a docstring |
| Tasks | ☐ feat(accounts): create accounts/decorators.py with role_required(role) decorator using functools.wraps → commit: "feat(accounts): add role_required decorator for role-based view protection" ☐ test(accounts): manually verify parent cannot access /calendar/ (student view) and gets redirected → commit: "test(accounts): verify role_required decorator redirects incorrect roles" |
| Definition of Done | Decorator exists and documented. Parent blocked from student views. Student blocked from parent views. Unauthenticated → login. |

| S1.4 — Parent Creates Student Login |  |
| --- | --- |
| User Story | As a parent, I can create login credentials for my child so that my child can log in and see their own calendar without having their own email address |
| LO Covered | LO3.1, LO3.3 |
| Acceptance Criteria | ✓ A form exists for parent to set child's username and password ✓ Submitting creates a User + UserProfile(role="student") linked to the Child record ✓ Username must be unique — duplicate shows validation error ✓ After creation, parent sees the credentials summary and a success message ✓ Student can log in using these credentials ✓ Only parents can access this form (role_required) |
| Tasks | ☐ feat(accounts): create StudentCreationForm with username and password fields → commit: "feat(accounts): add student credential creation form" ☐ feat(scheduler): add create_student_login view — POST creates User+UserProfile, links to Child.student_user → commit: "feat(scheduler): add view for parent to create student login credentials" ☐ feat(templates): create scheduler/create_student_login.html with form and credential display → commit: "feat(templates): add student credential creation page" ☐ feat(scheduler): add URL /children/<child_id>/create-login/ and wire to view → commit: "feat(scheduler): wire student login creation URL" |
| Definition of Done | Parent creates student credentials. Student can log in. UserProfile(role=student) created. Linked to Child record. |

| S1.5 — Add Child Profile |  |
| --- | --- |
| User Story | As a parent, I can add my child's profile to my account so that the system knows which school year my child is in and can present the right curriculum |
| LO Covered | LO2.2, LO2.4, LO3.3 |
| Acceptance Criteria | ✓ Form has: first name, birth month (dropdown 1–12), birth year, school year (dropdown Year 1–11), academic year start date ✓ Submitting valid data creates a Child record linked to the logged-in parent ✓ School year dropdown is populated from the distinct years in the curriculum data ✓ After creation, parent is redirected to the subject selection page for that child ✓ Form shows validation errors inline for missing/invalid fields ✓ Only parents can access this form (role_required) ✓ W3C HTML validation passes |
| Tasks | ☐ feat(scheduler): create ChildForm ModelForm with all required fields and clean validation → commit: "feat(scheduler): add Child creation form with school year validation" ☐ feat(scheduler): create add_child view — GET renders form, POST creates Child and redirects to subject selection → commit: "feat(scheduler): add child profile creation view" ☐ feat(templates): create scheduler/add_child.html with crispy form → commit: "feat(templates): add child profile creation page" ☐ feat(scheduler): add /children/add/ URL → commit: "feat(scheduler): wire add child URL" |
| Definition of Done | Child created linked to parent. Redirects to subject selection. Validation errors shown. Role protected. |

| S1.6 — Subject Selection Page |  |
| --- | --- |
| User Story | As a parent, I can select which Oak National Academy subjects my child will study and set a weekly lesson pace for each so that the scheduling engine has everything it needs to generate the full timetable |
| LO Covered | LO2.2, LO2.4, LO1.1 |
| Acceptance Criteria | ✓ Page shows all subjects available for the child's school year, grouped by key stage ✓ Each subject row has: checkbox, subject name, total lesson count badge, lessons-per-week spinner (1–5) ✓ At least one subject must be selected — selecting none and submitting shows an error ✓ Lessons-per-week spinner is disabled until the subject checkbox is ticked ✓ Submitting creates EnrolledSubject records for each selected subject ✓ Each EnrolledSubject is automatically assigned a colour from the predefined palette ✓ After submission, parent is redirected to a confirmation page before scheduling ✓ Only parents can access this page |
| Tasks | ☐ feat(scheduler): create subject_selection view — queries distinct subjects for child school year, builds context → commit: "feat(scheduler): add subject selection view with Oak curriculum data" ☐ feat(scheduler): on POST, create EnrolledSubject records with colour assignment logic → commit: "feat(scheduler): implement EnrolledSubject creation with automatic colour assignment" ☐ feat(templates): create scheduler/subject_selection.html — grouped accordion, checkbox+spinner per subject → commit: "feat(templates): add subject selection page with grouped subjects and pace spinners" ☐ style: add JS to enable/disable spinner when checkbox toggled → commit: "style: add JS to link subject checkbox with pace spinner state" ☐ feat(scheduler): add /children/<child_id>/subjects/ URL → commit: "feat(scheduler): wire subject selection URL" |
| Definition of Done | EnrolledSubjects created with colour. Spinner disabled until checkbox ticked. Minimum 1 subject enforced. Role protected. |

| S1.7 — Schedule Generation — Service Function |  |
| --- | --- |
| User Story | As a developer, I can implement the schedule generation algorithm as a standalone, testable service function so that the 180-day lesson timetable can be generated and tested independently of the web layer |
| LO Covered | LO1.4, LO7.1 |
| Acceptance Criteria | ✓ A function `generate_schedule(child, enrolled_subjects)` exists in scheduler/services.py ✓ It builds a list of exactly 180 weekday dates starting from child.academic_year_start ✓ It distributes lessons round-robin respecting each subject's lessons_per_week limit ✓ It uses bulk_create with batch_size=500 for performance ✓ It returns the total count of ScheduledLesson records created ✓ It has a full docstring explaining parameters, algorithm, and return value ✓ Running on a 3-subject selection produces the expected number of ScheduledLessons |
| Tasks | ☐ feat(scheduler): create scheduler/services.py with generate_schedule function skeleton and docstring → commit: "feat(scheduler): add generate_schedule service function skeleton" ☐ feat(scheduler): implement step 1 — build 180 weekday dates from start date → commit: "feat(scheduler): implement school day list generation (180 weekdays)" ☐ feat(scheduler): implement step 2 — build per-subject lesson queues from curriculum → commit: "feat(scheduler): implement lesson queue builder per enrolled subject" ☐ feat(scheduler): implement step 3 — distribute lessons round-robin with weekly limits → commit: "feat(scheduler): implement round-robin lesson distribution with weekly pace" ☐ feat(scheduler): implement step 4 — bulk_create ScheduledLesson objects → commit: "feat(scheduler): implement bulk_create for ScheduledLesson records" |
| Definition of Done | Function exists in services.py with full docstring. Runs without error. Returns correct count. Uses bulk_create. |

| S1.8 — Schedule Generation — Web Layer |  |
| --- | --- |
| User Story | As a parent, I can click "Generate Schedule" and have all lessons automatically distributed across the school year so that my child immediately has a complete, day-by-day timetable without any manual work |
| LO Covered | LO2.2, LO2.3 |
| Acceptance Criteria | ✓ A "Generate Schedule" page shows a summary (child name, subjects, lesson counts) before confirming ✓ Clicking Confirm calls generate_schedule() and creates all ScheduledLesson records ✓ A success message appears: "[Child name]'s schedule is ready — [N] lessons scheduled across 180 days" ✓ If a schedule already exists for the child, it is deleted and regenerated cleanly ✓ After generation, parent is redirected to their dashboard ✓ The view is protected with role_required("parent") |
| Tasks | ☐ feat(scheduler): create generate_schedule_view — GET shows summary, POST calls service and bulk creates → commit: "feat(scheduler): add schedule generation view calling service function" ☐ feat(scheduler): add idempotency — delete existing ScheduledLessons before regenerating → commit: "feat(scheduler): add idempotent schedule regeneration" ☐ feat(scheduler): add success message with lesson count on completion → commit: "feat(scheduler): add schedule generation success notification" ☐ feat(templates): create scheduler/generate_schedule.html with summary and confirm button → commit: "feat(templates): add schedule generation confirmation page" ☐ feat(scheduler): add /children/<child_id>/schedule/generate/ URL → commit: "feat(scheduler): wire schedule generation URL" |
| Definition of Done | Schedule generates. Correct count shown in message. Re-running cleans old schedule. Parent redirected to dashboard. |

| S1.9 — Parent Dashboard |  |
| --- | --- |
| User Story | As a parent, I can see a dashboard showing a summary of my child's learning progress so that I always have a quick overview without needing to drill into the calendar |
| LO Covered | LO1.1, LO3.3 |
| Acceptance Criteria | ✓ Dashboard shows: child's name, school year, total lessons scheduled, lessons completed this week, overall completion percentage ✓ If parent has no children, a prompt to "Add your first child" is shown ✓ Dashboard is at / (root URL) for logged-in parents ✓ Dashboard is protected with role_required("parent") ✓ Page is responsive and passes W3C validation |
| Tasks | ☐ feat(scheduler): create parent_dashboard view — queries child + schedule stats, builds context → commit: "feat(scheduler): add parent dashboard view with progress summary" ☐ feat(templates): create scheduler/parent_dashboard.html with summary cards → commit: "feat(templates): add parent dashboard with child summary cards" ☐ feat(edutrack): update root URL / to redirect based on role (parent→dashboard, student→calendar) → commit: "feat(edutrack): add role-based root URL redirect" |
| Definition of Done | Dashboard renders. Stats accurate. Empty state shown if no children. Role protected. Responsive. |

| S1.10 — Sprint 1 Deployment |  |
| --- | --- |
| User Story | As a developer, I can deploy Sprint 1 to Heroku and verify all auth and scheduling flows work in production so that the live app reflects all Sprint 1 work and is smoke-tested before Sprint 2 begins |
| LO Covered | LO6.1 |
| Acceptance Criteria | ✓ All Sprint 1 migrations run on Heroku without errors ✓ Parent registration flow works end-to-end on the live URL ✓ Login and logout work correctly ✓ Child creation and subject selection work ✓ Schedule generation completes and shows correct success message ✓ No 500 errors encountered during smoke test |
| Tasks | ☐ chore: push all Sprint 1 commits to GitHub → commit: "chore: complete Sprint 1 — auth, child setup, and scheduling" ☐ chore: git push heroku main; heroku run python manage.py migrate → (Heroku CLI) ☐ chore: smoke test all Sprint 1 flows on live URL → commit: "chore: verify Sprint 1 deployment — auth and scheduling live" |
| Definition of Done | All Sprint 1 features work on live Heroku URL. No errors. Migration clean. |

SPRINT 2 — Calendar View, Lesson Tracking & Evidence Days 7–9 · Epics E4, E5 & E6 · 12 Stories · Target: Full student lesson interaction loop

Sprint Goal: The student sees a Syllabird-style weekly calendar with coloured subject cards. Clicking a card opens a modal. The student can mark lessons complete, set mastery scores, add notes, upload evidence files, and reschedule. The parent sees a read-only version of the same calendar.

| S2.1 — Weekly Calendar View — Structure |  |
| --- | --- |
| User Story | As a student, I can see a weekly calendar showing all my scheduled lessons organised into Monday to Friday columns so that I always know exactly what I am supposed to study on any given day |
| LO Covered | LO1.1, LO3.3 |
| Acceptance Criteria | ✓ Calendar shows 5 columns: Monday through Friday with dates shown below day names ✓ Each column shows all ScheduledLessons for that day for the logged-in student ✓ The current week is displayed by default ✓ Week start/end dates are shown in the page header ✓ The calendar view is at /calendar/ ✓ The view is protected with role_required("student") ✓ If no lessons are scheduled, an empty state message is shown ✓ W3C HTML validation passes |
| Tasks | ☐ feat(tracker): create calendar view — compute week dates from query param, query ScheduledLessons, build day-keyed context → commit: "feat(tracker): add weekly calendar view with day-keyed lesson context" ☐ feat(templates): create tracker/calendar.html — 5-column CSS grid, day header with date, lesson card placeholder → commit: "feat(templates): add weekly calendar template with 5-column day grid" ☐ feat(tracker): add /calendar/ and /calendar/<year>/<week>/ URLs → commit: "feat(tracker): wire calendar URLs with week navigation parameters" |
| Definition of Done | Calendar renders for current week. Days show correct dates. Student lessons appear in correct columns. Empty state shown when no lessons. |

| S2.2 — Calendar Week Navigation |  |
| --- | --- |
| User Story | As a student, I can navigate to previous and next weeks on the calendar so that I can review past lessons and see upcoming lessons without leaving the calendar |
| LO Covered | LO1.1 |
| Acceptance Criteria | ✓ Previous week (←) and Next week (→) arrow buttons are visible in the calendar header ✓ A "Today" button returns to the current week from any other week ✓ Clicking navigation reloads the calendar showing the correct week ✓ The active week dates are always shown in the header ✓ URL updates to reflect the week being viewed (e.g. /calendar/2024/36/) |
| Tasks | ☐ feat(tracker): update calendar view to accept year/week URL params; compute prev/next week values → commit: "feat(tracker): add week navigation logic to calendar view" ☐ feat(templates): add prev/next arrow links and Today button to calendar header → commit: "feat(templates): add week navigation controls to calendar header" |
| Definition of Done | Prev/Next navigation works. Today button returns to current week. URL reflects active week. |

| S2.3 — Subject Colour Cards |  |
| --- | --- |
| User Story | As a student, I can see each lesson card styled with its subject's colour so I can instantly identify which subject it belongs to so that the calendar is visually clear and I never confuse subjects |
| LO Covered | LO1.1 |
| Acceptance Criteria | ✓ Each lesson card has a coloured header band using the EnrolledSubject.colour_hex value ✓ The card body is white with the lesson title and completion status badge ✓ Subject colours are consistent — the same subject always uses the same colour across all views ✓ Cards are readable (sufficient contrast between text and background on both header and body) ✓ Completed lessons show a "✓ Complete" badge; skipped show "Skipped"; pending show no badge ✓ CSS variables in custom.css drive the subject colours (not inline styles) |
| Tasks | ☐ style: update calendar template to apply inline style="--subject-colour: {{ enrolled_subject.colour_hex }}" on each card → commit: "style: apply subject colour system to calendar lesson cards" ☐ style: add card CSS — coloured header band, white body, completion status badges → commit: "style: add lesson card styles with coloured header and status badges" |
| Definition of Done | Subject colours display correctly. Same subject = same colour. Status badges visible. Contrast readable. |

| S2.4 — Lesson Detail Modal — Structure |  |
| --- | --- |
| User Story | As a student, I can click on any lesson card to see the lesson details in a modal panel so that I can interact with a lesson without leaving the calendar view |
| LO Covered | LO1.1, LO2.2 |
| Acceptance Criteria | ✓ Clicking any lesson card opens a Bootstrap Modal ✓ Modal header shows the lesson title with the subject colour background ✓ Modal shows: lesson title, unit name, subject name, scheduled date, Oak lesson URL (opens in new tab) ✓ Modal shows current completion status and mastery score if set ✓ Modal has a close (×) button that dismisses it cleanly ✓ Modal opens without page reload ✓ Accessibility: modal has aria-labelledby and aria-modal="true" |
| Tasks | ☐ feat(tracker): create lesson_detail view returning lesson data as JSON for AJAX → commit: "feat(tracker): add lesson detail JSON endpoint for modal population" ☐ feat(templates): add Bootstrap Modal markup to calendar.html with empty placeholder sections → commit: "feat(templates): add lesson detail modal structure to calendar template" ☐ style: add JS in calendar.js — on card click, fetch lesson detail, populate modal, show modal → commit: "style: add calendar.js with card click handler and modal population" |
| Definition of Done | Clicking a card opens modal with correct lesson data. Oak URL opens in new tab. Modal closes cleanly. ARIA attributes present. |

| S2.5 — Mark Lesson Complete or Skip |  |
| --- | --- |
| User Story | As a student, I can mark a lesson as complete or skip it directly from the modal so that my progress is recorded in real time and my parent can see what I have done |
| LO Covered | LO2.2, LO2.3 |
| Acceptance Criteria | ✓ Modal has "Mark Complete" and "Skip" buttons ✓ Clicking "Mark Complete" creates/updates LessonLog with status="complete" and sets completed_at ✓ Clicking "Skip" creates/updates LessonLog with status="skipped" ✓ After the action, a Django success message appears without full page reload (flash on next navigation) ✓ The calendar card badge updates to reflect the new status without full page reload ✓ The action is protected — only the student who owns the lesson can update it ✓ CSRF token is included in all AJAX POST requests |
| Tasks | ☐ feat(tracker): create update_lesson_status view — POST with status param, get_or_create LessonLog, save → commit: "feat(tracker): add lesson status update view for complete and skip actions" ☐ feat(tracker): add /lessons/<scheduled_id>/update/ URL → commit: "feat(tracker): wire lesson status update URL" ☐ style: update calendar.js — add click handlers for Complete/Skip buttons, AJAX POST, update card badge on response → commit: "style: add AJAX lesson status update with immediate card badge refresh" |
| Definition of Done | Complete and Skip update LessonLog. Card badge updates immediately. CSRF present. Ownership enforced. |

| S2.6 — Mastery Score |  |
| --- | --- |
| User Story | As a student, I can set a mastery score of Green, Amber, or Red for any completed lesson so that I and my parent can track how confident I feel about each topic |
| LO Covered | LO2.2 |
| Acceptance Criteria | ✓ Modal shows three mastery buttons: 🟢 Green, 🟡 Amber, 🔴 Red ✓ Currently selected mastery is visually highlighted ✓ Clicking a mastery button saves the score to LessonLog.mastery via AJAX POST ✓ Mastery can be changed after initial selection ✓ Mastery score is shown on the lesson card as a small coloured dot ✓ Saving mastery shows a brief success indicator in the modal |
| Tasks | ☐ feat(tracker): create update_mastery view — POST with mastery param, updates LessonLog → commit: "feat(tracker): add mastery score update view" ☐ feat(tracker): add /lessons/<scheduled_id>/mastery/ URL → commit: "feat(tracker): wire mastery update URL" ☐ style: update modal template — add mastery button group with active state styling → commit: "style: add mastery score selector to lesson modal" ☐ style: update calendar.js — AJAX POST on mastery button click, update active state, add card dot → commit: "style: add AJAX mastery update with card indicator" |
| Definition of Done | Mastery saves via AJAX. Active state shows current selection. Card shows coloured dot. Can be changed. |

| S2.7 — Student Notes on Lesson |  |
| --- | --- |
| User Story | As a student, I can add a personal note to any lesson recording my thoughts or what I learned so that my portfolio reflects my genuine engagement with the lesson content |
| LO Covered | LO2.2, LO2.4 |
| Acceptance Criteria | ✓ Modal has a Notes textarea ✓ Notes are saved to LessonLog.student_notes via form POST ✓ Notes save successfully on form submit with a success message ✓ Notes are loaded and displayed when the modal reopens for the same lesson ✓ Notes textarea has a max character count indicator (1000 chars) ✓ Empty notes are valid (notes field is optional) |
| Tasks | ☐ feat(tracker): create save_notes view — POST, update LessonLog.student_notes, return JSON success → commit: "feat(tracker): add student notes save view" ☐ feat(tracker): update lesson_detail view to include existing notes in JSON response → commit: "feat(tracker): include saved notes in lesson detail endpoint" ☐ feat(templates): add notes textarea with char counter to lesson modal → commit: "feat(templates): add notes textarea to lesson modal with character counter" ☐ style: update calendar.js — on modal open populate notes; on save POST notes, show confirm → commit: "style: add notes population and save handler in calendar.js" |
| Definition of Done | Notes save and reload correctly. Empty notes valid. Char limit shown. Success message appears. |

| S2.8 — Reschedule a Lesson |  |
| --- | --- |
| User Story | As a student, I can move a lesson to a different date if I could not complete it on the scheduled day so that my calendar stays accurate and my parent sees a realistic view of my progress |
| LO Covered | LO2.2, LO2.3 |
| Acceptance Criteria | ✓ Modal has a "Reschedule" section with a date picker ✓ Selecting a new date and clicking Reschedule updates ScheduledLesson.scheduled_date ✓ The lesson disappears from its original day and appears on the new date ✓ Only future dates can be selected ✓ A success message confirms the reschedule ✓ Rescheduled date is stored in LessonLog.rescheduled_to for audit trail |
| Tasks | ☐ feat(tracker): create reschedule_lesson view — POST with new date, update ScheduledLesson.scheduled_date → commit: "feat(tracker): add lesson reschedule view" ☐ feat(tracker): add /lessons/<scheduled_id>/reschedule/ URL → commit: "feat(tracker): wire lesson reschedule URL" ☐ feat(templates): add reschedule date picker section to lesson modal → commit: "feat(templates): add reschedule section with date picker to lesson modal" ☐ style: update calendar.js — on reschedule submit POST, close modal, reload calendar week → commit: "style: add reschedule AJAX handler in calendar.js" |
| Definition of Done | Reschedule updates date. Lesson moves on calendar. Future-only date picker. Success message. Audit trail in LessonLog. |

| S2.9 — Parent Read-Only Calendar |  |
| --- | --- |
| User Story | As a parent, I can view my child's weekly calendar to see what they have completed and how they are progressing so that I can monitor my child's learning without needing to log in as the student |
| LO Covered | LO3.3, LO1.1 |
| Acceptance Criteria | ✓ Parent can access /parent/calendar/<child_id>/ to view a child's calendar ✓ The calendar renders identically to the student view but with no action buttons ✓ Parent cannot mark lessons complete, set mastery, or upload files ✓ Parent can navigate weeks using the same prev/next controls ✓ Accessing a child that does not belong to the logged-in parent returns 403 ✓ View is protected with role_required("parent") |
| Tasks | ☐ feat(tracker): create parent_calendar view — same query as student calendar, passes is_readonly=True to context → commit: "feat(tracker): add parent read-only calendar view" ☐ feat(templates): update calendar.html — conditionally render action buttons only if not is_readonly → commit: "feat(templates): hide action buttons in read-only calendar mode" ☐ feat(tracker): add /parent/calendar/<child_id>/ and week navigation URLs → commit: "feat(tracker): wire parent calendar URLs with ownership check" |
| Definition of Done | Parent sees calendar. No action buttons visible. Wrong child returns 403. Role protected. |

| S2.10 — Evidence File Upload |  |
| --- | --- |
| User Story | As a student, I can upload a file as evidence of my work for any lesson so that my portfolio contains tangible proof of my learning that my parent can include in LA reports |
| LO Covered | LO2.2 |
| Acceptance Criteria | ✓ Modal has an evidence upload section with a file input ✓ Accepted file types: image/*, application/pdf, .doc, .docx ✓ Uploading a file creates an EvidenceFile record linked to the LessonLog ✓ File is stored in Cloudinary, not on the server ✓ A success message appears after upload ✓ The modal shows the count of uploaded files for the lesson ✓ Invalid file types show a clear validation error |
| Tasks | ☐ feat(tracker): create upload_evidence view — POST with file, create LessonLog if not exists, save EvidenceFile → commit: "feat(tracker): add evidence file upload view with Cloudinary storage" ☐ feat(tracker): add /lessons/<scheduled_id>/upload/ URL → commit: "feat(tracker): wire evidence upload URL" ☐ feat(templates): add file upload form to lesson modal evidence section → commit: "feat(templates): add evidence upload form to lesson modal" ☐ feat(tracker): update lesson_detail endpoint to include evidence file count → commit: "feat(tracker): include evidence file count in lesson detail endpoint" |
| Definition of Done | Files upload to Cloudinary. EvidenceFile record created. Invalid types rejected. Count shown in modal. |

| S2.11 — Evidence File List and Delete |  |
| --- | --- |
| User Story | As a student, I can see all files I have uploaded for a lesson and delete any that are incorrect so that I can maintain a clean, accurate evidence portfolio |
| LO Covered | LO2.2 |
| Acceptance Criteria | ✓ Modal evidence section lists all uploaded files with: filename, upload date, delete button ✓ Clicking delete removes the EvidenceFile record and the file from Cloudinary ✓ A confirmation prompt appears before deletion ✓ File list updates without full page reload after delete ✓ Only the student who uploaded the file can delete it |
| Tasks | ☐ feat(tracker): create delete_evidence view — POST, verify ownership, delete EvidenceFile + Cloudinary resource → commit: "feat(tracker): add evidence file deletion view with ownership check" ☐ feat(tracker): add /evidence/<file_id>/delete/ URL → commit: "feat(tracker): wire evidence delete URL" ☐ feat(tracker): update lesson_detail endpoint to include file list (id, filename, uploaded_at) → commit: "feat(tracker): include evidence file list in lesson detail endpoint" ☐ style: update calendar.js — render file list in modal, add delete handler with confirm prompt → commit: "style: add evidence file list rendering and delete handler to modal" |
| Definition of Done | File list renders in modal. Delete removes from DB and Cloudinary. Ownership enforced. Confirm before delete. |

| S2.12 — Sprint 2 Deployment |  |
| --- | --- |
| User Story | As a developer, I can deploy Sprint 2 to Heroku and verify the full student interaction loop works in production so that the live app reflects the complete calendar and lesson tracking system |
| LO Covered | LO6.1 |
| Acceptance Criteria | ✓ All Sprint 2 migrations run without errors ✓ Student can log in, see calendar, click a card, mark it complete ✓ Mastery score saves correctly ✓ Notes save and reload on modal reopen ✓ File upload works with real Cloudinary in production ✓ Parent can see child's calendar in read-only mode ✓ No 500 errors during smoke test |
| Tasks | ☐ chore: push all Sprint 2 commits to GitHub → commit: "chore: complete Sprint 2 — calendar, tracking, and evidence" ☐ chore: git push heroku main; heroku run python manage.py migrate → (Heroku CLI) ☐ chore: smoke test full student loop and parent calendar on live URL → commit: "chore: verify Sprint 2 deployment — full lesson interaction loop live" |
| Definition of Done | All Sprint 2 features work on live Heroku URL. File upload works via Cloudinary in production. No errors. |

SPRINT 3 — Reports, Stripe, Testing, Docs & Final Deploy Days 10–12 · Epics E7, E8 & E9 · 10 Stories · Target: Production-ready, all LOs evidenced

Sprint Goal: LA-ready PDF reports generate and download. The LA share token link works without login. Stripe pricing UI is complete (feature-flagged). All automated tests pass. README is complete. Final production deployment is verified with DEBUG=False.

| S3.1 — Report Creation Form |  |
| --- | --- |
| User Story | As a parent, I can fill in a form to specify the parameters of an LA evidence report for my child so that I can generate a report covering exactly the period and detail level the LA requires |
| LO Covered | LO2.2, LO2.4 |
| Acceptance Criteria | ✓ Form has: date from, date to, report type (Summary / Full Portfolio) ✓ Summary = lesson counts per subject with completion percentages ✓ Full Portfolio = all of the above plus student notes and mastery scores per lesson ✓ Date range validates: date_from must be before date_to ✓ A preview section shows how many completed lessons fall in the selected range ✓ Only parents can access this form (role_required) ✓ W3C validation passes |
| Tasks | ☐ feat(reports): create ReportForm ModelForm with date range and type fields → commit: "feat(reports): add report creation form with date range and type selection" ☐ feat(reports): create create_report view — GET renders form, POST computes preview stats → commit: "feat(reports): add report creation view with preview stats" ☐ feat(templates): create reports/create_report.html with form and live preview → commit: "feat(templates): add report creation page with parameter form" ☐ feat(reports): add /reports/create/<child_id>/ URL → commit: "feat(reports): wire report creation URL" |
| Definition of Done | Form renders. Date validation works. Preview shows correct lesson count. Role protected. |

| S3.2 — PDF Report Generation and Download |  |
| --- | --- |
| User Story | As a parent, I can generate and download a professional PDF evidence report for the Local Authority so that I can submit a polished, credible document to the LA without any manual formatting work |
| LO Covered | LO2.2 |
| Acceptance Criteria | ✓ Confirming the report form generates a PDF using xhtml2pdf ✓ PDF includes: child name, school year, date range, subject-by-subject lesson breakdown ✓ Full Portfolio type also includes student notes and mastery colour indicators per lesson ✓ PDF is uploaded to Cloudinary and a download link is returned ✓ A Report record is created in the database ✓ The PDF renders correctly (no broken layout, no missing content) ✓ Download link in the browser triggers a file download |
| Tasks | ☐ feat(reports): create HTML report template reports/pdf_template.html (clean, print-ready layout) → commit: "feat(reports): add HTML-to-PDF report template" ☐ feat(reports): implement PDF generation in reports/services.py using xhtml2pdf → commit: "feat(reports): implement PDF generation service with xhtml2pdf" ☐ feat(reports): update create_report view POST — generate PDF, upload to Cloudinary, create Report record → commit: "feat(reports): wire PDF generation and Cloudinary upload to report creation view" ☐ feat(reports): create report_detail view with download link → commit: "feat(reports): add report detail view with PDF download link" ☐ feat(reports): add /reports/<report_id>/ URL → commit: "feat(reports): wire report detail URL" |
| Definition of Done | PDF downloads. Contains correct content. Both report types render correctly. Report record in DB. File in Cloudinary. |

| S3.3 — LA Share Token Link |  |
| --- | --- |
| User Story | As a parent, I can share a report with the Local Authority via a secure link that does not require them to log in so that the LA officer can view the report instantly without creating an account |
| LO Covered | LO3.1, LO3.3 |
| Acceptance Criteria | ✓ Report detail page shows a "Share with LA" button that reveals a copy-able URL ✓ The URL contains the report's UUID share token (e.g. /reports/share/550e8400-e29b.../) ✓ Visiting the token URL shows the report in read-only mode without requiring login ✓ If the token has expired (token_expires_at is set and in the past), the page shows a 403 with a clear message ✓ If the token UUID is invalid (not found in DB), the page returns a 404 ✓ The share URL page has no navbar login/logout links — it is a standalone page |
| Tasks | ☐ feat(reports): create token_report_view — validate UUID, check expiry, render read-only report → commit: "feat(reports): add LA share token view with UUID validation and expiry check" ☐ feat(reports): add /reports/share/<uuid:token>/ URL → commit: "feat(reports): wire LA share token URL" ☐ feat(templates): create reports/shared_report.html — standalone template, no navbar auth links → commit: "feat(templates): add standalone LA report template for token sharing" ☐ feat(templates): update report_detail.html to show share URL with copy button → commit: "feat(templates): add share URL display and copy button to report detail page" |
| Definition of Done | Token URL renders report without login. Expired token = 403. Invalid UUID = 404. Share URL copyable from parent view. |

| S3.4 — Stripe Pricing Page |  |
| --- | --- |
| User Story | As a parent, I can see the available subscription plans and understand what each tier includes so that I can make an informed decision about upgrading to the Pro plan |
| LO Covered | LO1.1 |
| Acceptance Criteria | ✓ Pricing page at /payments/plans/ shows two tiers: Free and Pro ✓ Free tier: 1 child, no PDF export, no LA sharing ✓ Pro tier: unlimited children, PDF reports, LA sharing, priority support ✓ Page is accessible without login ✓ A "Choose Pro" button is present on the Pro card ✓ Page is responsive and visually clear ✓ W3C validation passes |
| Tasks | ☐ feat(payments): create pricing_page view and minimal template → commit: "feat(payments): add Stripe pricing page with Free and Pro tier comparison" ☐ feat(templates): create payments/pricing.html with two-column card layout → commit: "feat(templates): add pricing page template with tier comparison" ☐ style: style pricing cards with feature lists and CTA buttons → commit: "style: add pricing card styles with feature lists" ☐ feat(payments): add /payments/plans/ URL → commit: "feat(payments): wire pricing page URL" |
| Definition of Done | Pricing page renders. Two tiers visible. Feature comparison clear. Responsive. W3C valid. |

| S3.5 — Stripe Checkout Stub |  |
| --- | --- |
| User Story | As a parent, I can click "Choose Pro" and be taken through a payment flow so that the subscription upgrade journey is complete even if live payments are not yet active |
| LO Covered | LO1.1, LO2.2 |
| Acceptance Criteria | ✓ Clicking "Choose Pro" takes logged-in parent to a checkout page ✓ Checkout page shows plan summary and a Stripe.js payment form ✓ STRIPE_ENABLED=False setting shows a "Test Mode — Payments Disabled" banner instead of the real form ✓ A success page exists at /payments/success/ confirming subscription activation ✓ Subscription status is stored on UserProfile (settable in admin for testing) ✓ Unsubscribed parents attempting to generate a report see a friendly upgrade prompt |
| Tasks | ☐ feat(payments): create checkout view — checks STRIPE_ENABLED flag, renders form or test banner → commit: "feat(payments): add Stripe checkout view with STRIPE_ENABLED feature flag" ☐ feat(payments): add subscription_active field to UserProfile; update UserAdmin to show it → commit: "feat(payments): add subscription_active field to UserProfile" ☐ feat(payments): create success view and template → commit: "feat(payments): add payment success page" ☐ feat(reports): add subscription gate to report creation — redirect to pricing if not subscribed → commit: "feat(reports): add subscription check to report generation flow" ☐ feat(payments): add /payments/checkout/ and /payments/success/ URLs → commit: "feat(payments): wire checkout and success URLs" |
| Definition of Done | Pricing page links to checkout. Feature flag shows test banner. Success page exists. Subscription gate on reports. |

| S3.6 — Automated Python Tests |  |
| --- | --- |
| User Story | As a developer, I can write automated Django TestCase tests covering all critical application paths so that the codebase is verified to work correctly and the test suite demonstrates testing competency |
| LO Covered | LO4.1, LO8.4 |
| Acceptance Criteria | ✓ At least 11 test cases exist across accounts/, scheduler/, tracker/, reports/ test files ✓ All tests pass when running python manage.py test ✓ Tests cover: schedule algorithm, LessonLog CRUD, role access control, report token validation, registration role assignment ✓ Each test file has a module-level docstring explaining what is being tested ✓ Test fixtures or setUp methods create the required data — no reliance on live database |
| Tasks | ☐ test(scheduler): test_schedule_generates_correct_count, test_no_weekend_lessons, test_respects_weekly_pace → commit: "test(scheduler): add automated tests for schedule generation algorithm" ☐ test(tracker): test_lesson_log_created_on_complete, test_status_update_complete_to_skip → commit: "test(tracker): add automated tests for lesson log CRUD" ☐ test(accounts): test_registration_creates_parent_role, test_student_blocked_from_parent_views, test_parent_blocked_from_student_views → commit: "test(accounts): add role-based access control tests" ☐ test(reports): test_valid_token_renders_report, test_invalid_token_returns_404, test_expired_token_returns_403 → commit: "test(reports): add share token validation tests" |
| Definition of Done | All tests pass. Minimum 11 test cases. Each test is independent. Test files have docstrings. |

| S3.7 — README — UX and Design Documentation |  |
| --- | --- |
| User Story | As a developer, I can document the UX design process, wireframe decisions, and design rationale in the README so that the assessor can follow the design thinking from concept to implementation |
| LO Covered | LO1.5 |
| Acceptance Criteria | ✓ README has a UX Design section with: project purpose, target user, design rationale ✓ Wireframe descriptions (text-based or image) for: calendar view, lesson modal, dashboard, subject selection ✓ Explanation of Syllabird as UX reference and how EduTrack adapts the pattern ✓ Colour system documented with token names and their usage ✓ Accessibility decisions documented (semantic HTML, ARIA, contrast) ✓ README is written in clear, professional English |
| Tasks | ☐ docs(readme): add UX Design section with purpose, user personas, design rationale → commit: "docs(readme): add UX design section with wireframes and rationale" ☐ docs(readme): add colour system documentation and accessibility decisions → commit: "docs(readme): add design system and accessibility documentation" |
| Definition of Done | README UX section complete. Wireframes described. Design rationale clear. Colour system documented. |

| S3.8 — README — Testing Documentation |  |
| --- | --- |
| User Story | As a developer, I can document all testing procedures and results in the README so that the assessor can see exactly what was tested, how, and what the results were |
| LO Covered | LO4.3 |
| Acceptance Criteria | ✓ README has a Testing section with: testing approach (automated + manual) ✓ Automated test table: test name, what it tests, pass/fail result ✓ Manual JS test table: scenario, steps, expected result, actual result, pass/fail ✓ Python test command shown: python manage.py test ✓ At least 8 manual JS test scenarios documented with actual results filled in |
| Tasks | ☐ docs(readme): add Testing section with automated test results table → commit: "docs(readme): add automated test results to testing section" ☐ docs(readme): add manual JavaScript test table with all 8 scenarios and results → commit: "docs(readme): add manual JS test table with pass/fail results" |
| Definition of Done | Testing section complete. All automated tests documented with results. Manual JS table fully filled in. |

| S3.9 — README — Deployment and AI Reflection |  |
| --- | --- |
| User Story | As a developer, I can document the full deployment process and reflect on AI tool usage in the README so that the assessor can reproduce the deployment and understand how AI contributed to development |
| LO Covered | LO6.2, LO8.1, LO8.2, LO8.3, LO8.4, LO8.5 |
| Acceptance Criteria | ✓ README has a Deployment section with step-by-step Heroku instructions ✓ Deployment section covers: environment variables, Procfile, migrate, seed, createsuperuser ✓ README has an AI Tools section covering all 5 LO8 criteria ✓ AI section includes: code creation examples, debugging examples, optimisation examples, unit test generation, workflow reflection ✓ AI reflections focus on outcomes, not detailed prompt logs ✓ README has a Features section listing all implemented features with screenshots or descriptions |
| Tasks | ☐ docs(readme): add Deployment section with full step-by-step Heroku guide → commit: "docs(readme): add complete deployment documentation" ☐ docs(readme): add AI Tools section covering all LO8 criteria with outcome-focused reflections → commit: "docs(readme): add AI tools reflection covering LO8 criteria" ☐ docs(readme): add Features section with feature descriptions → commit: "docs(readme): add features section to readme" ☐ docs(readme): final README review — check all sections, fix any gaps → commit: "docs(readme): finalise README — all sections complete" |
| Definition of Done | Deployment section complete and accurate. AI section covers all LO8 points. README is final. |

| S3.10 — Final Production Deployment |  |
| --- | --- |
| User Story | As a developer, I can perform the final production deployment with all security settings verified so that the submitted application is fully functional, secure, and meets all deployment requirements |
| LO Covered | LO6.1, LO6.2, LO6.3, LO5.2 |
| Acceptance Criteria | ✓ git push heroku main succeeds with no build errors ✓ All migrations run cleanly on production database ✓ DEBUG=False confirmed in production ✓ ALLOWED_HOSTS does not include "*" ✓ No passwords or sensitive information anywhere in the git repository ✓ The live URL smoke test passes all Sprint exit criteria ✓ python manage.py test passes locally before final push ✓ Final commit message is: "chore: final production deployment — EduTrack v1.0" |
| Tasks | ☐ chore: run python manage.py test — all tests pass → commit: "test: final test run — all tests passing before production deploy" ☐ chore: final security audit — check .env not committed, DEBUG=False, ALLOWED_HOSTS correct → commit: "chore: final security audit before production deployment" ☐ chore: git push heroku main; heroku run python manage.py migrate → (Heroku CLI) ☐ chore: full smoke test — register parent, add child, select subjects, generate schedule, student login, mark lessons, generate report, download PDF, test LA token URL → commit: "chore: final production deployment — EduTrack v1.0" |
| Definition of Done | App deployed. All features working. DEBUG=False. No secrets in repo. All tests pass. Smoke test complete. |

# 7. GitHub Projects Setup Guide

Set up GitHub Projects before writing a single line of code. The board structure must match this plan.

## 7.1 Create the Board

| Step | Action |
| --- | --- |
| 1 | Go to your GitHub repo → Projects tab → New Project → Board view |
| 2 | Name it "EduTrack Development Board" |
| 3 | Create 5 columns: 📋 Backlog ¦ 🔍 In Analysis ¦ 🛠 In Progress ¦ 👀 In Review ¦ ✅ Done |
| 4 | Create 9 Milestones (epics): E1 Foundation ¦ E2 Auth ¦ E3 Scheduling ¦ E4 Calendar ¦ E5 Tracking ¦ E6 Evidence ¦ E7 Reports ¦ E8 Payments ¦ E9 Testing & Deploy |
| 5 | Create Labels: must-have ¦ should-have ¦ frontend ¦ backend ¦ devops ¦ testing ¦ docs ¦ sprint-0 ¦ sprint-1 ¦ sprint-2 ¦ sprint-3 |

## 7.2 Creating Issues for Each Story

Each story in this document becomes a GitHub Issue. Use this template exactly:

TITLE: [STORY-ID] Story Title e.g. [S0.1] Django Project Skeleton BODY: ## User Story As a [role], I can [action] so that [outcome]. ## Acceptance Criteria - [ ] Criterion 1 - [ ] Criterion 2 - [ ] Criterion 3 ## Tasks - [ ] Task 1 → commit: "type(app): description" - [ ] Task 2 → commit: "type(app): description" ## Definition of Done Specific DoD statement for this story. ## LO Coverage LO1.1, LO3.3 (etc.) MILESTONE: E2 Auth & Roles (the epic this story belongs to) LABELS: must-have, backend, sprint-1

Create ALL issues before starting Sprint 0. Start all stories in Backlog. Move them through columns as you work.

## 7.3 Story Status Flow

| Status | When To Move There |
| --- | --- |
| 📋 Backlog | Issue created, not yet started |
| 🔍 In Analysis | You have opened this document to review the story, AC, and tasks |
| 🛠 In Progress | First task commit has been made for this story |
| 👀 In Review | All tasks committed; running through AC checklist |
| ✅ Done | All AC pass; DoD confirmed; issue closed |

# 8. Sprint-End Smoke Test Checklists

Run these manually on the live Heroku URL at the end of each sprint before marking the sprint complete.

## Sprint 0 Smoke Test

| # | Test | Result |
| --- | --- | --- |
| 1 | Visit live Heroku URL — page loads with no 500 error |  |
| 2 | Visit /admin/ — login page appears |  |
| 3 | Log into /admin/ with superuser — admin panel shows all 7 models |  |
| 4 | Check curriculum.Lesson count in admin — should be ~10,055 |  |
| 5 | Check DEBUG setting — should be False in production |  |
| 6 | Check no .env file is in GitHub repository |  |

## Sprint 1 Smoke Test

| # | Test | Result |
| --- | --- | --- |
| 1 | Register as a new parent — form submits, UserProfile(role=parent) created, redirected to dashboard | pass / fail |
| 2 | Log in with parent credentials — navbar shows first name + "Parent" badge | pass / fail |
| 3 | Log out — redirected to homepage, navbar shows login/register links | pass / fail |
| 4 | Add a child — form submits, redirected to subject selection | pass / fail |
| 5 | Select 3 subjects with different paces — EnrolledSubjects created | pass / fail |
| 6 | Click Generate Schedule — success message shows correct lesson count | pass / fail |
| 7 | Create student login from parent account | pass / fail |
| 8 | Log in as student — navbar shows "Student" badge, redirected to calendar | pass / fail |
| 9 | As student, attempt to visit /children/ — redirected with error | pass / fail |
| 10 | As parent, attempt to visit /calendar/ — redirected with error | pass / fail |

## Sprint 2 Smoke Test

| # | Test | Result |
| --- | --- | --- |
| 1 | Log in as student — calendar shows current week with coloured subject cards | pass / fail |
| 2 | Navigate to next week and back to today | pass / fail |
| 3 | Click a lesson card — modal opens with lesson title and Oak URL | pass / fail |
| 4 | Click Mark Complete — card badge updates to Complete without page reload | pass / fail |
| 5 | Click Green mastery — card shows green dot, modal shows Green selected | pass / fail |
| 6 | Type a note and save — note reappears when modal is reopened | pass / fail |
| 7 | Upload an image file — success message, file count increments in modal | pass / fail |
| 8 | Delete an uploaded file — confirm prompt, file removed | pass / fail |
| 9 | Reschedule a lesson — lesson disappears from original day, appears on new date | pass / fail |
| 10 | Log in as parent — view child calendar, confirm no action buttons visible | pass / fail |

## Final Sprint 3 Smoke Test

| # | Test | Result |
| --- | --- | --- |
| 1 | As parent, navigate to report creation — form renders | pass / fail |
| 2 | Set date range and type Summary — preview shows lesson count | pass / fail |
| 3 | Generate report — PDF downloads successfully | pass / fail |
| 4 | Copy LA share URL — open in incognito/private window — report renders without login | pass / fail |
| 5 | Test invalid token URL (/reports/share/invalid-uuid/) — 404 page | pass / fail |
| 6 | Visit /payments/plans/ — pricing page renders with Free and Pro tiers | pass / fail |
| 7 | Click Choose Pro — checkout page loads (shows test mode banner) | pass / fail |
| 8 | Run python manage.py test locally — all tests pass | pass / fail |
| 9 | Confirm DEBUG=False in Heroku config vars | pass / fail |
| 10 | Check GitHub repo — no .env file, no passwords in any committed file | pass / fail |

# 9. Quick Reference

## Story Index

| ID | Story Title | Epic | Sprint | LO |
| --- | --- | --- | --- | --- |
| S0.1 | Django Project Skeleton | E1 | Sprint 0 | LO5.1, LO5.2 |
| S0.2 | Database Configuration | E1 | Sprint 0 | LO1.2, LO5.2 |
| S0.3 | Cloudinary Storage Config | E1 | Sprint 0 | LO6.1, LO6.3 |
| S0.4 | All Seven Custom Models | E1 | Sprint 0 | LO1.2, LO2.1, LO7.1 |
| S0.5 | Django Admin Configuration | E1 | Sprint 0 | LO3.1 |
| S0.6 | Oak Curriculum Seed Command | E1 | Sprint 0 | LO1.4 |
| S0.7 | Base Template & Static Files | E1 | Sprint 0 | LO1.1 |
| S0.8 | First Heroku Deployment | E1 | Sprint 0 | LO6.1, LO6.2, LO6.3 |
| S1.1 | Parent Registration | E2 | Sprint 1 | LO3.1, LO2.4 |
| S1.2 | Login, Logout & Login State | E2 | Sprint 1 | LO3.1, LO3.2 |
| S1.3 | Role-Based Access Decorator | E2 | Sprint 1 | LO3.3, LO1.4 |
| S1.4 | Parent Creates Student Login | E2 | Sprint 1 | LO3.1, LO3.3 |
| S1.5 | Add Child Profile | E3 | Sprint 1 | LO2.2, LO2.4 |
| S1.6 | Subject Selection Page | E3 | Sprint 1 | LO2.2, LO2.4 |
| S1.7 | Schedule Generation — Service | E3 | Sprint 1 | LO1.4, LO7.1 |
| S1.8 | Schedule Generation — Web | E3 | Sprint 1 | LO2.2, LO2.3 |
| S1.9 | Parent Dashboard | E3 | Sprint 1 | LO1.1, LO3.3 |
| S1.10 | Sprint 1 Deployment | E3 | Sprint 1 | LO6.1 |
| S2.1 | Weekly Calendar — Structure | E4 | Sprint 2 | LO1.1, LO3.3 |
| S2.2 | Calendar Week Navigation | E4 | Sprint 2 | LO1.1 |
| S2.3 | Subject Colour Cards | E4 | Sprint 2 | LO1.1 |
| S2.4 | Lesson Detail Modal | E5 | Sprint 2 | LO1.1, LO2.2 |
| S2.5 | Mark Lesson Complete / Skip | E5 | Sprint 2 | LO2.2, LO2.3 |
| S2.6 | Mastery Score | E5 | Sprint 2 | LO2.2 |
| S2.7 | Student Notes | E5 | Sprint 2 | LO2.2, LO2.4 |
| S2.8 | Reschedule a Lesson | E5 | Sprint 2 | LO2.2, LO2.3 |
| S2.9 | Parent Read-Only Calendar | E5 | Sprint 2 | LO3.3, LO1.1 |
| S2.10 | Evidence File Upload | E6 | Sprint 2 | LO2.2 |
| S2.11 | Evidence File List & Delete | E6 | Sprint 2 | LO2.2 |
| S2.12 | Sprint 2 Deployment | E6 | Sprint 2 | LO6.1 |
| S3.1 | Report Creation Form | E7 | Sprint 3 | LO2.2, LO2.4 |
| S3.2 | PDF Report Generation | E7 | Sprint 3 | LO2.2 |
| S3.3 | LA Share Token Link | E7 | Sprint 3 | LO3.1, LO3.3 |
| S3.4 | Stripe Pricing Page | E8 | Sprint 3 | LO1.1 |
| S3.5 | Stripe Checkout Stub | E8 | Sprint 3 | LO1.1, LO2.2 |
| S3.6 | Automated Python Tests | E9 | Sprint 3 | LO4.1, LO8.4 |
| S3.7 | README — UX Documentation | E9 | Sprint 3 | LO1.5 |
| S3.8 | README — Testing Docs | E9 | Sprint 3 | LO4.3 |
| S3.9 | README — Deploy & AI Reflection | E9 | Sprint 3 | LO6.2, LO8 |
| S3.10 | Final Production Deployment | E9 | Sprint 3 | LO6.1, LO6.3 |

## The Golden Rules

| # | Rule |
| --- | --- |
| 1 | Never write code until the story's AC and tasks have been read in full |
| 2 | One task = one commit. Never batch multiple tasks into a single commit. |
| 3 | Never commit to GitHub with a failing manage.py check |
| 4 | Never hardcode any secret, URL, or credential. All config via python-decouple. |
| 5 | Never move a story to Done until all its acceptance criteria are manually verified |
| 6 | Deploy to Heroku at the end of every sprint — never let deployment drift more than 3 days |
| 7 | If a story feels too big mid-sprint, split it into two stories. Do not rush the AC. |
| 8 | Update the README in the same sprint as the feature — never leave it to the end |
| 9 | Every Python function must have a docstring before the story is marked Done |
| 10 | When in doubt about scope: do less, do it well, commit it clean. |